## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | CB 03/20/2024
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | CB 03/20/2024
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Fail | At this point, we do not have this functionality implemented, at it will just show a blank page. CB
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | CB 03/20/2024
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | CB 03/20/2024
As a User I want to be able to log in SO THAT I can add needs to my cart and checkout needs | GIVEN I want to log in and attempt to do so WHEN there is an account with my information, THEN I will be signed in to my account and be able to view and edit my cart and a status code of 200 (OK) is returned | Pass | CB 03/20/2024
| GIVEN I want to log in and attempt to do so WHEN there is NO account with my information THEN I am prompted to make an account and the status code of 404 (NOT FOUND) is returned | Pass | CB 03/20/2024. A 404 message is returned, however the page doesn’t do anything to tell the user. Although 404 is returned, we should add a message to the login page telling the user that the login failed.
| GIVEN when I am in my cart, WHEN I click the remove from cart button, THEN the item should be removed from my cart. | Fail | There seems to be a bug that when pressing remove from cart, the item appears to be removed, but when you go back into the cart again the item it not removed. It actually seems to double the amount in there. CB
As a Helper I want to logout SO THAT I can return at a later time to purchase items | GIVEN I as a user click logout WHEN I am a user who is logged in THEN I get sent back to the log in screen and my data (cart) is saved and a stats report of () is returned. | Pass | CB 03/20/2024. Cart saves.
AS a Developer I WANT to submit a request to get the the needs in the cupboard whose name contains the given text, SO THAT I have access to only that subset of needs. | GIVEN I search a need object with a given text WHEN at least one need with the given name exists THEN the system should return a list of only the needs whose name contains the given text and a status code of 200 (OK) | Pass | CB 03/20/2024
| GIVEN I search a need object with a given text WHEN a need with the given name does **NOT** exist THEN the system should return an empty list of needs and a status code of 200 (OK) | Pass | CB 03/20/2024
AS a user, I WANT to see the name, cost, and description of an item SO THAT I can see more information about a single item. | GIVEN I click on a need WHEN I am logged in as a user, THEN I should be brought to a details page for that item, showing the name, price, and description of the item. | Pass | CB 03/20/2024
| GIVEN I click on a need that does not exist WHEN I am a user, I should be brought to a page that says that the item it not found and be returned at 404. | Fail | Currently, if you go to a detail page that does not exist, it just brings the user to a blank page. There should be a message here telling the user the item was not found, and an option to go back. CB