## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | Did fail, fixed and passes as of 03/21/2024. CB | Pass | OL - 4/3/23
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
As a User I want to be able to log in SO THAT I can add needs to my cart and checkout needs | GIVEN I want to log in and attempt to do so WHEN there is an account with my information, THEN I will be signed in to my account and be able to view and edit my cart and a status code of 200 (OK) is returned | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| GIVEN I want to log in and attempt to do so WHEN there is NO account with my information THEN I am prompted to make an account and the status code of 404 (NOT FOUND) is returned | Pass | CB 03/20/2024. A 404 message is returned, however the page doesn’t do anything to tell the user. Although 404 is returned, we should add a message to the login page telling the user that the login failed. | Pass | OL - 4/3/23
| GIVEN when I am in my cart, WHEN I click the remove from cart button, THEN the item should be removed from my cart. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
As a Helper I want to logout SO THAT I can return at a later time to purchase items | GIVEN I as a user click logout WHEN I am a user who is logged in THEN I get sent back to the log in screen and my data (cart) is saved and a stats report of () is returned. | Pass | CB 03/20/2024. Cart saves. | Pass | OL - 4/3/23
AS a Developer I WANT to submit a request to get the the needs in the cupboard whose name contains the given text, SO THAT I have access to only that subset of needs. | GIVEN I search a need object with a given text WHEN at least one need with the given name exists THEN the system should return a list of only the needs whose name contains the given text and a status code of 200 (OK) | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| GIVEN I search a need object with a given text WHEN a need with the given name does **NOT** exist THEN the system should return an empty list of needs and a status code of 200 (OK) | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
AS a user, I WANT to see the name, cost, and description of an item SO THAT I can see more information about a single item. | GIVEN I click on a need WHEN I am logged in as a user, THEN I should be brought to a details page for that item, showing the name, price, and description of the item. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| GIVEN I click on a need that does not exist WHEN I am a user, I should be brought to a page that says that the item it not found and be returned at 404. | Pass | Failed previously, but fixed as of 03/21/2024. CB | Pass | OL - 4/3/23
As a admin I want to be able to login so that I can add, edit, or remove items from the cupboard. | GIVEN that I log in as admin, WHEN I log in, THEN I should be brought to a separate page instead of the user page. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| GIVEN that I log in as admin, WHEN I add an item, THEN it should get added to the cupboard. | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| GIVEN that I log in as admin, WHEN I remove an item, THEN it should get removed from the cupboard | Pass | CB 03/20/2024 | Pass | OL - 4/3/23
| GIVEN that I log in as admin, WHEN I edit an item, THEN it should be reflected in the cupboard. | Pass | Failed previously because we did not implement this yet, but works as of 03/20/2024. CB | Pass | OL - 4/3/23
Sprint 3
As a admin, I want to be able to set a priority for a need so that I can enable the users to search for items based on priority. | GIVEN that when I log in as admin, WHEN I add an item, THEN I should be able to set the priority for the need. |  |  | Pass | OL - 4/3/23
| GIVEN that when I log in as admin, WHEN I edit an item, THEN I should be able to edit the priority for that need. |  |  | Pass | OL - 4/3/23
| GIVEN that when I log in as admin, WHEN I log in, THEN I should see the item priority listed under the needs |  |  | Pass | OL - 4/3/23
As a user, I want to to able to see the priority for items and sort by the priority. | GIVEN that when I log in as a user, WHEN I log in, THEN I should see the item priority listed under the needs |  |  | Pass | OL - 4/3/23
| GIVEN that when I log in as a user, WHEN I log in, THEN I should be able to sort needs by their priority and fund the one that is the most important. |  |  | Pass | Done as of 4-7-24. CB
As a user, I want to be able to add needs to my cart and checkout from the cart. | GIVEN that when I am logged in as a user, WHEN I press the add to cart button, THEN the item should be added to the cart |  |  | Pass | OL - 4/3/23
| GIVEN that when I am logged in as a user, WHEN I press the checkout button, THEN I should be able to checkout (items removed from current cart). |  |  | Pass | CB 4-8-24
| GIVEN that when I am logged in as a user, WHEN I press the checkout button, then I should be brought to a thank you page thanking the user for their purchase. |  |  | Pass | CB 4-8-24
As a user, I want to be able to have a nice user interface so that I can use the U-Fund application easily. | GIVEN then when I log in as a user, WHEN I am on the main page, THEN I should see the needs displayed nicely with all the data surronding them shown. |  |  | Pass | OL - 4/3/23
| GIVEN that when I log in as an admin, WHEN I log in, THEN I should see a nice user interface for adding or editing items |  |  | Pass | OL - 4/3/23